## Roadmap Overview
SAL — Security Audit Log Tool ¦ 3-Stage Implementation Roadmap
Feature prioritization, effort assessment and brainstorming workbook.
Stage | Name | Objective | Representative Capabilities | Complexity | Sequence | Primary Value
Stage 1 | Audit Automation Foundation | Reliable SM19/SM20 MVP and reusable foundation. | SM20 extraction; SM19 visibility; transaction/user search; exports; dashboard; scheduling; audit trail | Low–Medium | Deliver first | Immediate consultant time savings
Stage 2 | Security Intelligence & Correlation | Add identity, access, GRC and behavioral context. | User timelines; critical/after-hours activity; PFCG/SUIM; Firefighter; cross-system; anomaly rules | Medium–High | Build on Stage 1 | Investigation and access intelligence
Stage 3 | Full SAL Investigation Platform | Enterprise investigation, monitoring and AI-assisted security. | Natural language; playbooks; risk scoring; cases; correlation; AI summaries; alerts; cloud/SIEM | High–Very High | Final target | End-to-end investigation platform

## Feature Backlog
SAL Detailed Feature Backlog
Primary brainstorming sheet: functionality, implementation, dependencies, effort, ease, risk and acceptance criteria.
ID | Stage | Feature | Objective | Suggested Implementation | Inputs / Sources | Outputs | Dependencies | Complexity | Effort | Ease | Priority | Risks / Considerations | Acceptance Criteria
S1-01 | Stage 1 | SAP Connectivity & Secure Configuration | Secure reusable SAP connectivity. | Approved RFC/API abstraction; dedicated least-privileged user; secrets outside code. | SAP connection metadata | Connection/session health | Network; SAP auth; SDK/API | Medium | 1–2 weeks | Medium | P0 | Credentials; excessive auth; compatibility | Securely connect and validate system/client.
S1-02 | Stage 1 | SM20 Security Audit Log Extraction | Automate Security Audit Log retrieval. | Collector → parser → normalized events → DB; incremental checkpoints. | SM20 | Normalized events | SM20 logging; SAP auth | Medium | 2–4 weeks | Medium | P0 | Volume; duplicates; time zones; incomplete logging | Reconcile with validated SM20 test cases.
S1-03 | Stage 1 | SM19 Audit Configuration Visibility | Show what audit logging is configured to capture. | Timestamped configuration snapshots and baseline comparison. | SM19 configuration | Configuration status/gaps | Configuration read access | Medium | 1–2 weeks | Medium | P0 | Release differences; varying baseline | Show current config and traceable deviations.
S1-04 | Stage 1 | Normalized Audit-Event Database | Reusable searchable event foundation. | Relational DB, common schema, indexes, retention and provenance. | Normalized SM20 | Indexed event store | Database | Medium | 2–3 weeks | Medium | P0 | Volume; retention; sensitive data | Search stored events with source traceability.
S1-05 | Stage 1 | Transaction Usage Search | Answer FBL5N-type questions. | Validated query service with transaction/time/system/client filters and grouping. | Transaction events | Users; counts; first/last usage | SM20 transaction events | Low | 1–2 weeks | High | P0 | Start event does not prove process completion | Accurate FBL5N users/counts/timestamps.
S1-06 | Stage 1 | User Activity Search | Retrieve captured activity for a user. | User-centric query template over event store. | User + events | Chronological activity | Event store | Low | 1–2 weeks | High | P0 | Historical identity ambiguity | Search user activity by time/event type.
S1-07 | Stage 1 | Search Filters | Combine system/client/user/transaction/event/time filters. | Common validated query object. | Event fields | Filtered results | Indexes; time-zone rules | Low | 3–5 days | High | P0 | Time-zone errors | Filters are consistent and reproducible.
S1-08 | Stage 1 | Excel / CSV Export | Audit-ready consultant outputs. | Standard export schema with scope, time, sources and detail. | SAL results | XLSX/CSV | Query engine | Low | 3–5 days | High | P0 | Sensitive exported data | Export matches on-screen result and scope.
S1-09 | Stage 1 | Basic Security Dashboard | Quick audit overview. | Aggregated metrics with drill-down. | Normalized events | KPIs/charts | Event store | Low–Medium | 1–2 weeks | High | P1 | Incomplete coverage may mislead | Each KPI has defined scope/formula.
S1-10 | Stage 1 | Scheduled Collection | Refresh SAL data automatically. | Scheduler with checkpoints, retries and idempotency. | Collector config | Run status | Scheduler | Medium | 1–2 weeks | Medium | P1 | Missed windows; duplicates; SAP load | Failed jobs resume safely.
S1-11 | Stage 1 | SAL Query & Audit Trail | Audit SAL usage. | Record user, query, export and configuration actions. | SAL metadata | Search/export history | Authentication/RBAC | Low–Medium | 1 week | High | P1 | Sensitive search history | Reconstruct who accessed which data.
S1-12 | Stage 1 | Critical Transaction Catalogue | Configurable risk classification. | Versioned catalogue including customer Z transactions. | Transaction catalogue | Risk category | Security governance | Low | 3–5 days | High | P1 | Criticality is organization-specific | Classification configurable/versioned.
S2-01 | Stage 2 | User Investigation Timeline | One chronological user security view. | Combine normalized events and drill to evidence. | User + events | Timeline | Stage 1 store | Medium | 2–3 weeks | Medium | P0 | Incomplete timeline | Every event links to evidence.
S2-02 | Stage 2 | After-Hours Detection | Flag activity outside business periods. | Rules using timestamps, weekends, holidays and calendars. | Events + calendar | Flagged events | Time-zone/calendar | Medium | 1–2 weeks | High | P0 | Not inherently malicious | Every flag explains the rule.
S2-03 | Stage 2 | Critical Transaction Monitoring | Focus on high-risk activity. | Apply catalogue to transaction events and dashboards. | Events + catalogue | Critical activity feed | S1-12 | Medium | 1–2 weeks | High | P0 | False positives | Show classification/rationale.
S2-04 | Stage 2 | User + Role Correlation | Compare activity with assigned access context. | Extract user-role and role transaction/menu context and correlate. | PFCG/SUIM + SM20 | Activity/access view | Role connectors | High | 3–5 weeks | Medium | P0 | Menu ≠ effective authorization | Avoid unsupported auth conclusions.
S2-05 | Stage 2 | SU01 / PFCG / SUIM Integration | Add identity/access context. | Read-only connectors for status/type/validity/roles/profiles. | SU01/PFCG/SUIM | User/access profile | SAP read auth | High | 3–5 weeks | Medium | P0 | Complex roles; sensitive data | Context timestamped/source-traceable.
S2-06 | Stage 2 | GRC Firefighter Integration | Correlate FF sessions with audit activity. | Normalize FF sessions; correlate by user/FFID/system/time; confidence. | GRC FF + SM20 | FF timeline | GRC access | High | 3–5 weeks | Medium | P0 | Decentralized GRC; sync differences | Map FF session to evidence with confidence.
S2-07 | Stage 2 | GRC ARM / ARA Context | Link activity to requests and SoD context. | Integrate approved GRC request/conflict sources. | GRC ARM/ARA | Request/SoD context | GRC connectors | High | 4–6 weeks | Medium–Low | P1 | Deployment-specific complexity | Context not treated as proof of misuse.
S2-08 | Stage 2 | Cross-System Investigation | One query across SAP landscape. | System registry + normalized multi-system execution. | Multiple systems | Landscape results | Multi-system connectors | High | 3–5 weeks | Medium | P0 | Clock/identity inconsistency | Clearly attribute system/client.
S2-09 | Stage 2 | Dormant / Unused Access Analysis | Find potentially excessive access. | Compare access inventory with observed usage. | Roles + events | Review candidates | Role mapping | Medium–High | 2–4 weeks | Medium | P1 | No observed use ≠ no business need | Use careful 'no observed usage' wording.
S2-10 | Stage 2 | Terminated User Monitoring | Detect post-termination activity. | Correlate effective termination time with events. | HR/identity + events | Exceptions | Authoritative termination source | Medium | 1–2 weeks | High | P0 | Feed delays; legitimate admin activity | Use explicit effective timestamp.
S2-11 | Stage 2 | Basic Anomaly Rules | Explainable behavioral deviations. | Rules for unusual transaction, spikes, technical-user interactive activity. | History + context | Anomaly indicators | Historical data | Medium | 2–4 weeks | Medium | P1 | Alert fatigue | Deterministic explanation for every anomaly.
S2-12 | Stage 2 | Investigation Report Generator | Consistent evidence-based reports. | Template scope, timeline, findings, evidence and limitations. | Investigation results | Report | Evidence model | Medium | 1–2 weeks | High | P1 | Narrative invention | Every finding links to evidence.
S3-01 | Stage 3 | Natural-Language Security Assistant | Conversational SAL queries. | LLM → constrained intent/query → validation/RBAC → query service. | Prompt + SAL metadata | Answer + evidence | Stable APIs; approved LLM | Very High | 5–8 weeks | Low | P0 | Hallucination; injection; leakage | Cannot bypass RBAC/supported queries.
S3-02 | Stage 3 | Investigation Playbooks | Automate repeatable investigations. | Versioned workflows for privileged/terminated/FF/suspicious transaction cases. | Playbook inputs | Repeatable investigation | Stage 2 rules | High | 3–5 weeks | Medium | P0 | Incomplete sources; workflow drift | Record steps, failures and evidence.
S3-03 | Stage 3 | Explainable Risk Scoring | Prioritize review. | Deterministic weighted scoring first; version factors/thresholds. | Correlated signals | Score + explanation | Mature rules | High | 4–6 weeks | Medium | P0 | False confidence | Score is explainable/reproducible.
S3-04 | Stage 3 | Security Case Management | Track investigation lifecycle. | Owner/status/notes/findings/evidence/reviewer/closure. | Investigation data | Case workspace | RBAC/audit trail | High | 4–6 weeks | Medium | P1 | Sensitive case data | Complete lifecycle and immutable refs.
S3-05 | Stage 3 | Multi-Source Correlation Engine | Combine SAP/GRC/cloud signals. | Common event/entity model; exact/inferred links; confidence. | Multiple sources | Unified timeline/graph | Mature connectors | Very High | 6–10+ weeks | Low | P0 | False correlations; identity mismatch | Visible join criteria/confidence.
S3-06 | Stage 3 | AI Investigation Summary | Evidence-grounded narrative. | Permission-checked evidence only; evidence refs for material claims. | Evidence set | Summary | Approved LLM | High | 3–5 weeks | Medium | P0 | Hallucination; leakage | No material claim without evidence.
S3-07 | Stage 3 | Continuous Monitoring & Alerts | Proactive detection. | Scheduled/continuous rules, severity, dedupe and notifications. | Incremental events | Alerts | Reliable ingestion | High | 4–6 weeks | Medium | P0 | Alert fatigue | Deduplicated evidence-linked alerts.
S3-08 | Stage 3 | Audit Evidence Packs | Defensible investigation package. | Bundle scope, sources, evidence refs, actions and report. | Cases/evidence | Evidence package | Integrity/retention | Medium–High | 2–4 weeks | Medium | P0 | Chain of custody | Reviewer reconstructs query/evidence.
S3-09 | Stage 3 | BTP / HANA / IAS / IPS Integrations | Extend beyond ABAP/GRC. | Source-specific connectors normalized to common event model. | Cloud/HANA/identity logs | Cross-platform events | Tenant/API permissions | Very High | 6–12+ weeks | Low | P1 | Different identity/API models | New source plugs in without core redesign.
S3-10 | Stage 3 | SIEM / SOC Integration | Feed findings to enterprise monitoring. | REST/syslog/message bus with SAL evidence references. | Alerts/cases | SIEM event/incident | Enterprise APIs | High | 3–6 weeks | Medium | P1 | Sensitive outbound data | Stable reference back to SAL.
S3-11 | Stage 3 | Advanced Behavioral Analytics | Complex anomaly detection. | Statistical baselines; ML only after data maturity. | Historical data | Anomaly scores/features | Large quality dataset | Very High | 8–12+ weeks | Low | P2 | Drift; bias; false positives | Validation and human review.
S3-12 | Stage 3 | Configuration Compliance | Continuous baseline assessment. | Versioned controls + config snapshots + exceptions. | SM19/config snapshots | Compliance dashboard | Governance baseline | High | 3–5 weeks | Medium | P1 | Baseline varies | Deviation cites control/version.

## Architecture
SAL Target Architecture
Stage 1 architecture should be intentionally reusable through Stage 3.
Layer | Purpose | Stage 1 | Stage 2 | Stage 3
User Interface | Search, dashboards, investigations, reports | Basic filters/UI | Investigation workspace | AI assistant + cases
Query / Intent | Validated query parameters | Structured filters | Query templates | Natural-language governed queries
Analytics | Aggregations and detections | Counts/grouping | Rules/correlations | Risk + advanced analytics
Normalization | Common event model | SM20 | Multiple SAP/GRC sources | Enterprise event/entity model
Connectors | Source data access | SM20/SM19 | SU01/PFCG/SUIM/GRC/FF | BTP/HANA/IAS/IPS/SIEM
Storage | Persist events/metadata | Relational DB | Indexed event store | Scalable security data platform
Reporting | Evidence and outputs | XLSX/CSV | Investigation reports | Evidence packs/compliance reports
Security | Protect/audit SAL | RBAC | Scoped RBAC | SSO/RBAC/SoD/full audit trail

## Technical Decisions
SAL Technical Decisions & Open Questions
Resolve these during discovery/technical spike.
Decision | Options | Recommended Direction | Why It Matters | Status
SAP connectivity | RFC/PyRFC; API; custom ABAP service | Evaluate RFC/API behind abstraction | Deployment/compatibility/licensing | Open
Runtime | Python; VM; container | Python MVP; plan managed/container deployment | Portability/operations | Open
Database | PostgreSQL; SQL Server; HANA; enterprise DB | Use supported relational DB | Volume/security/support | Open
UI | Streamlit; React + API; internal framework | Simple MVP UI; keep logic in service layer | Avoid UI lock-in | Open
LLM | Private/internal; approved API | Approved enterprise model only | Sensitive audit data | Stage 3
Scheduling | OS; Celery; enterprise scheduler | Job abstraction with retries/checkpoints | Reliable collection | Open
Secrets | Environment; vault | Vault for production | Credential security | Open
Authentication | Local; AD/LDAP; SSO | Enterprise SSO/AD | Lifecycle/auditability | Open
Deployment | Laptop; SAP OS; separate VM/container | Separate SAL host | Avoid SAP OS coupling | Open

## Risks & Controls
SAL Major Risks & Mitigations
Security, data quality and audit accuracy are first-class requirements.
Risk | Impact | Likelihood | Mitigation | Owner | Status
Insufficient SM20 logging | High | Medium | SM19 visibility + coverage warnings | SAP Security | Open
Large audit-log volume | High | High | Incremental extraction, indexing, retention | Engineering | Open
Timestamp/time-zone errors | High | Medium | Normalize time and synchronize clocks | Engineering/Basis | Open
Over-privileged SAL SAP account | Critical | Medium | Dedicated least-privileged user | SAP Security | Open
Sensitive data leakage | Critical | Medium | RBAC, encryption, retention, controlled exports | Security | Open
False positives | Medium–High | High | Deterministic rules and explanations | SAP Security | Open
AI hallucination | High | Medium | Evidence grounding and constrained query tools | AI/Security | Stage 3
Cross-system identity mismatch | High | Medium | Identity mapping + correlation confidence | Engineering/Security | Stage 2
SAP release differences | Medium–High | High | Version-aware connector adapters | Engineering/Basis | Open
Production performance impact | High | Medium | Throttling and incremental scheduled extraction | Basis/Engineering | Open
Feature creep | High | High | Stage gates and backlog prioritization | Product Owner | Open

## Discovery Questions
SAL Discovery & Brainstorming Questions
Workshop checklist for SAP Security, Basis, GRC, infrastructure and users.
Category | Question | Workshop Notes / Decision | Status
SAP Landscape | Which SAP releases/platforms must SAL support first? |  | Open
SAP Landscape | Which systems and clients are in the pilot? |  | Open
Connectivity | Is RFC connectivity permitted from the SAL host? |  | Open
Connectivity | Will NetWeaver RFC SDK/PyRFC be approved or should ABAP/API be used? |  | Open
Audit Logging | Which SM20 events are enabled in each target system? |  | Open
Audit Logging | What is current audit-log retention? |  | Open
Volume | Approximate daily event volume? |  | Open
Storage | Retain raw events, normalized events or both? |  | Open
Privacy | Which user/terminal/IP data may be stored and for how long? |  | Open
Risk | Which critical transactions should be in baseline? |  | Open
Time Rules | What business hours/weekends/holiday calendars apply? |  | Open
GRC | Is GRC centralized, decentralized or hybrid? |  | Open
GRC | Which Firefighter data is available and how is it reviewed? |  | Open
Identity | What source provides termination effective time? |  | Open
Use Cases | Which reports are prepared manually and how much effort do they consume? |  | Open
Use Cases | Which audit questions recur most often? |  | Open
Reporting | Which outputs are mandatory: Excel/CSV/PDF/dashboard/API? |  | Open
Authorization | Who may search logs and should access be scoped by system/client? |  | Open
Infrastructure | What SSO and secret-management services are available? |  | Open
AI | Is an approved internal/enterprise LLM available? |  | Open
Governance | What security/change review is required before production? |  | Open

## MVP & Stage Gates
SAL MVP Scope & Stage Gates
Prove trustworthy SM20 automation before advanced intelligence.
ID | MVP Capability | Stage | Priority | Status
MVP-01 | Secure connection to one SAP system/client | Stage 1 | Must Have | Not Started
MVP-02 | SM20 extraction for defined time window | Stage 1 | Must Have | Not Started
MVP-03 | SM19 configuration snapshot | Stage 1 | Must Have | Not Started
MVP-04 | Normalized audit-event database | Stage 1 | Must Have | Not Started
MVP-05 | FBL5N / transaction usage search | Stage 1 | Must Have | Not Started
MVP-06 | User activity search | Stage 1 | Must Have | Not Started
MVP-07 | System/client/user/transaction/event/time filters | Stage 1 | Must Have | Not Started
MVP-08 | Excel/CSV export | Stage 1 | Must Have | Not Started
MVP-09 | Basic activity dashboard | Stage 1 | Should Have | Not Started
MVP-10 | Query and extraction audit trail | Stage 1 | Must Have | Not Started
MVP-11 | Critical transaction catalogue | Stage 1 | Should Have | Not Started

## Query Catalogue
SAL Suggested Query Catalogue
Candidate use cases to guide product design, demos and acceptance testing.
Category | Example Query | Stage | Priority
Transaction Usage | Who used FBL5N in the last 7 days? | Stage 1 | P0
Transaction Usage | How many times was SE16N executed this month? | Stage 1 | P0
User Activity | Show all captured activity for USER123 yesterday. | Stage 1 | P0
Login Activity | Show failed logons for USER123 in the last 30 days. | Stage 1 | P1
Critical Activity | Show usage of critical transactions this week. | Stage 1–2 | P0
After Hours | Who executed critical transactions outside business hours? | Stage 2 | P0
Privileged Activity | Which privileged users executed SU01 this month? | Stage 2 | P0
Firefighter | Which FF sessions executed SE16N? | Stage 2 | P0
Role Correlation | Which users executed critical transactions and what roles do they have? | Stage 2 | P0
Unused Access | Which critical transactions assigned to users have no observed usage for 180 days? | Stage 2 | P1
Termination | Did any terminated user access SAP after termination? | Stage 2 | P0
Cross-System | Where did USER123 use FBL5N across the landscape? | Stage 2 | P0
Investigation | Investigate USER123 for unusual activity. | Stage 3 | P0
Risk | Show highest-risk user activity this week and explain why. | Stage 3 | P1
Playbook | Run privileged-user investigation for USER123. | Stage 3 | P0
Natural Language | Find suspicious activity involving SE16N last weekend. | Stage 3 | P0